## Sheet1
Week | Datum | Task | Assignee | Deadline
37
|  | Gather relevant teaching material | Tom
Meet with supervisor
Search literature for overview on connectivity analysis and causal models
|  | Read relevant teaching material | Ramon
Specify research topic
38
| 2013-09-17 | Discuss read material
| 2013-09-17 | Submit research topic |  | 15:00
Meet with supervisor
Write proposal
39
| 2013-09-17 | Research proposal draft finished |  | 10:30
| 2013-09-17 | Make proposal presentation (slides)
| 2013-09-27 | Presentation slides draft finished |  | 10:30
| 2013-09-27 | Submission of research proposal |  | 15:00
40
| 2013-10-01 | Rehearse proposal presentation
| 2013-10-01 | Submission of slides proposal presentation |  | 15:00
| 2013-10-02 | Proposal presentation |  | 15:00
50
| 2013-12-10 | Submission draft final paper |  | 15:00
51
| 2013-12-17 | Submission slides final presentation |  | 15:00
| 2013-12-18 | Final presentation |  | 15:00
2
| 2014-01-10 | Submission final paper |  | 15:00